Data Mining Course Project

Knowledge Discovery in Banking Datasets

Group of 4 Students, 14-Week Project

# 1. Project Overview

Students will apply the KDD (Knowledge Discovery in Databases) process end-to-end on real banking data to discover hidden patterns, segments, and association rules. Each group is assigned a different banking dataset covering domains such as credit risk, fraud, mortgage, customer churn, anti-money laundering, and institutional financial health. While datasets differ, all groups execute the same five-phase methodology.

The unifying theme across all groups is the banking domain. The unifying methodology is the KDD pipeline. The goal is discovery and interpretation of hidden knowledge, not prediction accuracy.

| Course | Data Mining |
| --- | --- |
| Group Size | 4 Students per Group |
| Duration | 14 Weeks |
| Dataset | Each group is assigned a different banking dataset. See Dataset Reference Document. |

# 2. Role Assignment

Each student holds a primary role throughout the project. However, each member should still contribute in each phase, especially in Phase 1 and Phase 5.

| Role | Responsibility |
| --- | --- |
| Data Engineer | Data collection, cleaning, integration, and preprocessing pipeline |
| Pattern Analyst | Association rule mining and frequent itemset discovery |
| Segmentation Specialist | Clustering analysis and entity profiling |
| Insight Communicator | Visualization, storytelling, final report, and presentation |

# 3. Project Phases

All groups execute the same 5 phases regardless of which dataset they are assigned. This ensures consistent assessment criteria and enables meaningful cross-group comparison at the end of the semester.

## Phase 1: Data Understanding and Preprocessing

| Owner | Data Engineer |
| --- | --- |
| Tasks |  |
|  | Explore the dataset: distributions, missing values, data types, and outliers |
|  | Apply data cleaning: handle nulls, fix inconsistencies, remove duplicates |
|  | Perform data transformation: normalization, encoding, and binning of continuous variables |
|  | Conduct feature selection using correlation analysis and entropy measures |
|  | Deliverable: Clean dataset file and Preprocessing Report |
| DM Concepts | Data quality, ETL pipeline, attribute types, noise handling, data transformation |
| Phase Goal | Produce a clean, analysis-ready dataset and document every preprocessing decision with justification. This phase establishes the factual foundation for all subsequent mining steps. |

## Phase 2: Segmentation via Clustering

| Owner | Segmentation Specialist |
| --- | --- |
| Tasks |  |
|  | Apply K-Means clustering to segment entities by behavioral or financial attributes |
|  | Use DBSCAN to identify outlier profiles and noise points within the data |
|  | Apply Hierarchical clustering and compare dendrograms across linkage methods |
|  | Determine optimal K using the Elbow Method and Silhouette Score |
|  | Profile each cluster: describe the entity type it represents and its distinguishing characteristics |
|  | Deliverable: Cluster profiles with full business interpretation |
| DM Concepts | Unsupervised pattern discovery, distance metrics, cluster validity indices, dendrogram analysis |
| Phase Goal | Identify naturally occurring groupings within the data and translate each group into a meaningful, named profile that describes real-world behavior or financial characteristics. |

## Phase 3: Association Rule Mining

| Owner | Pattern Analyst |
| --- | --- |
| Tasks |  |
|  | Discretize continuous variables into meaningful categorical groups |
|  | Apply the Apriori algorithm to discover frequent itemsets across the dataset |
|  | Generate association rules and compute Support, Confidence, and Lift for each |
|  | Filter rules to retain only meaningful, non-trivial, high-lift findings |
|  | Discover and document at least 10 rules with clear business interpretation |
|  | Deliverable: Rule table with ranked rules and business commentary |
| DM Concepts | Frequent pattern mining, rule interestingness measures, Apriori algorithm, Support, Confidence, Lift |
| Phase Goal | Surface co-occurrence patterns in the data that reveal non-obvious relationships between attributes, findings that cannot be seen through simple tabulation or aggregation. |

## Phase 4: Anomaly and Outlier Detection

| Owner | Data Engineer and Pattern Analyst |
| --- | --- |
| Tasks |  |
|  | Apply statistical methods (IQR, Z-score) to flag anomalous behaviors or values |
|  | Use Isolation Forest as a structural anomaly discovery tool |
|  | Cross-reference detected anomalies with cluster outliers from Phase 2 |
|  | Investigate each anomaly: data error, rare legitimate case, or potential risk signal? |
|  | Deliverable: Anomaly report with flagged records, explanation, and business interpretation |
| DM Concepts | Outlier analysis, statistical anomaly detection, Isolation Forest, anomaly typology |
| Phase Goal | Identify records that deviate substantially from the rest of the data and determine whether each deviation represents a data quality issue, an unusual but valid case, or a signal worth escalating. |

## Phase 5: Visualization and Knowledge Presentation

| Owner | Insight Communicator |
| --- | --- |
| Tasks |  |
|  | Build an interactive dashboard using Google Looker Studio or Python Dash (Tableau Public and Power BI are also options) |
|  | Visualize cluster maps, rule networks, outlier plots, and relevant distributions |
|  | Write a Knowledge Discovery Report translating all findings into plain business language |
|  | Answer the central question: What did we discover that was not already obvious from the raw data? |
|  | Deliverable: Dashboard, 10-minute group presentation, and final written report |
| DM Concepts | Data storytelling, knowledge presentation, dashboard design, business communication |
| Phase Goal | Communicate discovered knowledge to a non-technical audience clearly and convincingly. The measure of success is whether findings are actionable and non-trivial, not whether a model achieved high accuracy. |

# 4. Tech Stack

| Tool | Purpose |
| --- | --- |
| Python (pandas, mlxtend, scikit-learn) | Core analysis and mining algorithms |
| R | Core analysis and mining algorithms |
| Jupyter Notebook | Documentation and reproducible code |
| Matplotlib, Seaborn, Plotly | Data visualization and charts |
| Google Looker Studio or Python Dash | Interactive dashboard |
| GitHub | Collaboration and version control |

# 5. Grading Breakdown

# 6. Cross-Group Activity: Mining Expo

At the end of the semester, all groups present at a Mining Expo. Because every group applied the same 5-phase methodology to a different banking dataset, the expo creates structured ground for comparison without unfair overlap.

Each group addresses the following questions during their presentation:

- Which association rules were the most surprising, and why?

- Which clustering method produced the most interpretable segments for your dataset?

- What anomalies were found, and what do they suggest in a real banking context?

- How do your findings compare to what another group discovered in a different banking domain?

The expo reinforces that data mining techniques are domain-agnostic, but the meaning of discovered knowledge is always shaped by context.